# Sand Technologies — Forward Deployed Engineer Assignment

Candidate Submission: Rwanda Health Data Systems Engagement

This document addresses all four deliverables from the recruitment assignment. Assumptions are stated explicitly throughout, reflecting the intentional uncertainty of a Week 1 deployment scenario.

# Deliverable 1: Problem Decomposition and Scoping

## Section 1: Discovery Process

Who I would talk to in Week 1 and what I would ask:

MoH Director / DG Planning: What decisions does the Quarterly Bulletin inform? Who is the audience? What is the cost of a wrong or late bulletin?

DHIS2 system administrator: Which data elements feed the bulletin today? Export process, validation rules, known data quality issues, reporting timeliness SLAs.

District Health Officers (2–3 districts): How do you use facility status information today? What would 'real-time enough' mean given 3G constraints?

TB & HIV program leads: Patient matching workflow for co-infection, CommCare export capabilities, privacy constraints for record linkage.

HealthTrack EMR site champions (sample hospitals): Uptime, sync failures, what data never reaches DHIS2.

Paper facility reporting coordinators: Aggregation path from paper registers to DHIS2, error rates, lag.

Solutions Manager & Country Director: Political priorities, MoU success criteria, budget/timeline for 6-week sprint.

Patterns I would look for when decomposing 'our data is a mess':

Duplication — same indicator reported differently across DHIS2, EMR, Excel.

Timeliness gaps — bulletin uses Q-1 data compiled in week 4 of the new quarter.

Completeness — rural paper facilities missing from national aggregates.

Lineage blindness — no documented path from source register to bulletin table.

Decision latency — officers acting on 3-week-old DHIS2 vs operational reality.

Human bottleneck — 40 hrs/month manual Excel work = single point of failure.

Fragmented programs — TB/HIV silos with no shared patient identifier strategy.

What I would observe directly (not just hear about):

Sit in on one manual bulletin compilation session — count copy-paste steps.

Pull a live DHIS2 export and compare to published bulletin figures.

Visit one hospital (HealthTrack) and one rural paper facility same week.

Test connectivity and DHIS2 load time from a district office on 3G.

Review CommCare export format and whether patient IDs are linkable.

Check server uptime logs at 2–3 HealthTrack sites if accessible.

## Section 2: Problem Selection

Selected problem for 6-week sprint: Problem A — Automate the Quarterly Health Bulletin

Why Problem A over B and C:

Problem A — Highest near-term ROI: 40 hrs/month MoH staff time recovered; aligns with signed MoU language on 'decision-making capabilities'; uses DHIS2 data already aggregated nationally; achievable in 6 weeks with Sand Analytics Template Toolkit + custom ETL.

Problem B — Higher infrastructure risk (175 paper facilities, spotty connectivity, buggy EMRs). Better as Phase 2 once data pipeline trust exists. Health Atlas is the right product, but real-time facility status needs reliable ingestion first.

Problem C — Critical clinically, but requires patient identity resolution, governance, and TB/HIV program buy-in. 6 weeks is insufficient for ethical, compliant record linkage across CommCare instances.

Specific, measurable outcome (6-week sprint):

Automated bulletin covering Q1 metrics generated in < 30 minutes (vs 40 hrs manual).

HTML dashboard + exportable JSON/PDF consumed by MoH Planning unit.

Top 10 facilities, maternal indicators, performance scores, and QoQ trends — matching manual bulletin within 2% variance on pilot validation.

Explicitly OUT OF SCOPE (Sprint 1):

Real-time facility status / stockout mapping (Problem B).

Cross-program patient matching for TB/HIV co-infection (Problem C).

Full HealthTrack / OpenMRS integration — DHIS2 monthly aggregates only.

175 rural paper facility digitization.

Production HA deployment, SSO, or full Superset self-service rollout.

Key assumptions and Week 2 validation:

Assumption: DHIS2 exports contain sufficient fields for bulletin metrics today.

Validate: Compare prototype output to last published bulletin with MoH analyst.

Assumption: Performance scoring weights (40% timeliness / 60% completeness) match MoH expectations.

Validate: Workshop with Planning unit to confirm weighting and thresholds.

Assumption: Quarterly period labels (e.g. 2025Q1) align with DHIS2 period codes.

Validate: Pull metadata from DHIS2 API with IT admin.

Success metric:

MoH Planning lead signs off that automated bulletin replaces manual compilation for one full quarter, with ≤ 2% numeric variance and generation time < 30 minutes.

Fallback plan if harder than expected:

Week 3 checkpoint: If DHIS2 API access is delayed, continue with scheduled CSV imports (current prototype approach) and document API integration as Week 4–6 goal.

If performance scoring is contested, deliver raw timeliness/completeness tables first, defer composite score to MoH-configurable rules.

If PDF layout is blocked, ship HTML dashboard + JSON to Superset; manual PDF paste still saves > 30 hrs/month.

# Deliverable 2: Rapid Prototyping (Problem A)

## Section 1: Solution Design & Architecture

Architecture overview (data flow):

[DHIS2 / CSV Export] → [Ingestion Layer] → [HealthOS Data Models] → [Bulletin Metrics Engine] → [Outputs: HTML Dashboard | JSON API | Superset Feed]

Sand products leveraged:

HealthOS Data Models — standardize facility indicators (volume, ANC, deliveries) into a consistent schema before aggregation.

Analytics Template Toolkit (Apache Superset) — Phase 2 self-service exploration; prototype exposes JSON API for Superset dataset connection.

Health Insight Engine — future: anomaly flags on complication rate spikes (not in Week 2 prototype).

Custom build (justification):

Django bulletin service — MoH-specific metric definitions and bulletin layout; not available off-the-shelf.

Quarter-over-quarter trend logic with facility matching — custom business rules.

Performance score weighting — configurable MoH policy, built as code for sprint speed.

Build vs buy decisions:

| Component | Decision | Rationale |
| --- | --- | --- |
| Data warehouse | Buy — HealthOS | Reuse Sand transformations |
| BI dashboards | Buy — Superset templates | MoH analysts already need self-service |
| Bulletin orchestration | Build — Django | Specific MoH bulletin format |
| DHIS2 connector | Buy/adapt — existing HealthOS connector | Don't rebuild API client |
| Auth / SSO | Buy — MoH IdP integration | Defer to hardening phase |
| PDF generation | Build light — WeasyPrint/ReportLab | Or export to MoH Word template |

## Section 2: Working Prototype

Working Django project location: sand-fde-assignment/ (submitted with this document)

Prototype capabilities:

Reads sample DHIS2-like CSV: data/dhis2_facility_indicators.csv

Calculates: Top 10 facilities, maternal indicators, performance scores, QoQ trends

HTML dashboard at /

JSON API at /api/bulletin/

Export at /export/

Setup and run:

cd sand-fde-assignment

pip install -r requirements.txt

python manage.py migrate

python manage.py test

python manage.py runserver

Open http://127.0.0.1:8000/

Key code modules: bulletin/services.py (metrics), bulletin/views.py (dashboard/API), bulletin/templates/bulletin/dashboard.html (MoH-facing output).

## Section 3: Implementation Notes

Shortcuts taken to move fast:

CSV file instead of live DHIS2 API — avoids credential blockers in assignment timeframe.

Completeness proxied by non-zero mandatory fields — not full DHIS2 validation engine.

No database persistence — stateless compute from file; production would use Postgres.

JSON export instead of formatted PDF — proves data pipeline; PDF is template work.

Single consolidated CSV vs separate DHIS2 data element exports.

Week 3 demo — what works vs what is broken:

Works: All four bulletin sections render; period selector; API export; unit tests pass.

Broken / stubbed: Live DHIS2 pull, user authentication, scheduled monthly job, email distribution to districts, Superset dataset auto-refresh.

Fragile: Performance score weights are hard-coded; changing MoH policy requires code edit.

What I learned from building:

Even 'simple' bulletin automation touches data governance (what counts as complete?).

Separating metrics engine (services.py) from presentation enables Superset + HTML reuse.

Trend analysis exposes data quality issues early — facilities missing prior quarter surface immediately.

Django is sufficient for rapid FDE prototypes; migration path to SHOS services is clear.

# Deliverable 3: Production Hardening

## 1. DHIS2 integration & data freshness

Concern: Concern: CSV manual drops reintroduce the bottleneck and stale data risk.

Address: Address: Scheduled DHIS2 API pull via HealthOS connector; incremental sync; data freshness indicator on dashboard; alert if export > 21 days old.

## 2. Security & access control

Concern: Concern: Health data exposed without role-based access.

Address: Address: MoH SSO integration; district-level row filters; audit logging; HTTPS termination; secrets in vault not repo.

## 3. Data quality & validation

Concern: Concern: Proxy completeness scores may mis-rank facilities.

Address: Address: Implement DHIS2 validation rules; anomaly detection via Health Insight Engine; manual override workflow for district reviewers.

## 4. Reliability & observability

Concern: Concern: Silent pipeline failures during unreliable power/connectivity.

Address: Address: Idempotent ETL jobs; retry queues; dead-letter exports; monitoring dashboards; on-call runbook for MoH IT.

## 5. Output fidelity & distribution

Concern: Concern: JSON export is not the official bulletin format MoH publishes.

Address: Address: PDF generation matching MoH template; automated email to district lists; versioned bulletin archive; Superset dashboards for drill-down.

# Deliverable 4: Handover & Deployment

Three things to document for MoH IT:

Data pipeline runbook — DHIS2 credentials, cron schedule, failure recovery, contact escalation (Sand + MoH).

Metric definitions document — each bulletin field with formula, source data element, and known limitations.

Environment & deployment guide — server requirements, Django/Superset versions, backup strategy, and how to regenerate a bulletin manually.

Training plan:

| Audience | Topics | Format |
| --- | --- | --- |
| MoH Planning analysts | Running bulletin, interpreting trends, exporting PDF | 2 hr workshop |
| DHIS2 administrators | Data quality checks, validation rules, API tokens | Half-day technical |
| District health officers | Reading dashboard, identifying at-risk facilities | 1 hr webinar per zone |
| MoH IT / infrastructure | Deployment, monitoring, incident response | Hands-on with Sand FDE |

Exit criteria (transition out):

Two consecutive quarters generated by MoH staff without Sand FDE on-call support.

All runbooks and metric definitions signed off by MoH IT and Planning leads.

Superset dashboards adopted by at least 3 district officers with positive feedback.

Incident SLA agreed: MoH IT owns L1; Sand central FDE available for L2 escalations only.

Backlog for Problems B (Health Atlas) and C (program linkage) handed to Solutions Manager.

# Appendix: Submission Checklist

Scoping and design documents — this Word file

Working code with sample data — sand-fde-assignment/

README with setup/run instructions — README.md

Output demonstration — run server and open http://127.0.0.1:8000/